## Stakeholders
Jet EV Admin
Customer with EV

## PRD
Stakeholder | Action | Feature Group | Rules | Questions | Comments (IDT)
Customer with EV | As a customer I should be able to see locations of charging stations along with available chargers, availability and charging specifications at said stations | Charging station discovery and navigation
Customer with EV | As a customer I should be able to get navigation instructions to reach the selected charging station. | Charging station discovery and navigation
Customer with EV | Once at the station as a customer I should be able to identify the charger plugged in to my vehicle and start charging thorugh the web app | Charger Identification, Charger operations | Unique charger ID and QR
Customer with EV | As a customer I should be able to see the selected vehicle profile and available balance in the wallet. | Profiles, Wallet |  | What is the purpose of vehicle profile? Are we using this for analytics? | For collecting details, analytics and to detect if any specific problem related to vehicle arises...
Customer with EV | As a customer I should be able to see charge details particularly energy consumed. | Monitoring - User End
Customer with EV | As a customer I should be able to remotely stop charging and have the relevant charges deducted from my wallet. | Charger Operations, Wallet | Person cannot charge more than available balance.
Customer with EV | As a customer I should be able to see a report / invoice of the charge session that was just stopped | Invoice
Customer with EV | As a customer I should be able to top up my wallet | Wallet |  | What is the GST procedure for this? Do we charge GST at top up or charge at each session? | Currently used GST method (Similar procedure followed by other Chargers in Chargemod App)
Customer with EV | As a customer I should be able to see bill details for past transactions | Reports
Customer with EV | As a customer I should be able to CRUD vehicle profiles | Profiles
Jet EV Admin | As Admin I should be able to onboard chargers with details like 1. Charging Station Name and charging station location 2. Charger Name 3. Charger specification details | CSMS - Charger Management | Charger ID and OCPP URL should be auto generated
Jet EV Admin | As Admin I should be able to see a filterable list of added chargers along with status | CSMS - Charger Management
Jet EV Admin | As admin I should be able to update charger details, change its status or see charger specific logs | CSMS - Charger Management
Jet EV Admin | As admin I should be able to charger specific reports. Like uptime, energy delivered etc | CSMS - Reports
Jet EV Admin | As Admin I should be able to stop charging remotely. | CSMS - Charger Management
Jet EV Admin | As admin I should be able to see overall reports | CSMS - Reports
Jet EV Admin | As admin I should be able to see a list of customers, their details and wallet amounts | CSMS - CRM
Jet EV Admin | As admin I should be able to CRUD tariff rates | CSMS - ERP

## API FrontEnd
Grouping | Endpoint | Method | Description | Request Params | Response | Success Code | Error Codes
AUTHENTICATION & AUTHORIZATION | /api/admin/auth/login | POST | Admin login | Body: {email: string, password: string} | {access_token: string, refresh_token: string, user: AdminUser, expires_in: number} | 200 | 400, 422
AUTHENTICATION & AUTHORIZATION | /api/admin/auth/refresh | POST | Refresh access token | Body: {refresh_token: string} | {access_token: string, expires_in: number} | 200 | 401, 403
AUTHENTICATION & AUTHORIZATION | /api/admin/auth/me | GET | Get current admin | Headers: Authorization: Bearer {token} | {user: AdminUser, permissions: string[]} | 200 | 401, 403
AUTHENTICATION & AUTHORIZATION | /api/admin/auth/logout | POST | Logout admin | Headers: Authorization: Bearer {token} | {message: string} | 200 | 401
DASHBOARD OVERVIEW | /api/admin/dashboard/overview | GET | Key system metrics | Query: time_range?: string (1d,7d,30d,90d) | {total_chargers: number, online_chargers: number, active_sessions: number, total_energy_delivered: number, total_revenue: number, recent_transactions: Transaction[]} | 200 | 401, 403
DASHBOARD OVERVIEW | /api/admin/dashboard/stats | GET | Detailed statistics | Query: start_date?: string, end_date?: string | {charger_utilization: object, revenue_trend: object, energy_trend: object, top_stations: object} | 200 | 401, 403, 422
CHARGING STATION MANAGEMENT | /api/admin/stations | GET | List all stations | Query: page?: number, limit?: number, search?: string, sort?: string | {data: ChargingStation[], total: number, page: number, limit: number} | 200 | 401, 403, 422
CHARGING STATION MANAGEMENT | /api/admin/stations | POST | Create new station | Body: {name: string, latitude: number, longitude: number, address: string} | {station: ChargingStation, message: string} | 201 | 400, 401, 403, 422
CHARGING STATION MANAGEMENT | /api/admin/stations/{id} | GET | Get station details | Path: id: number | {station: ChargingStation, chargers: Charger[]} | 200 | 401, 403, 404
CHARGING STATION MANAGEMENT | /api/admin/stations/{id} | PUT | Update station | Path: id: number, Body: {name?: string, latitude?: number, longitude?: number, address?: string} | {station: ChargingStation, message: string} | 200 | 400, 401, 403, 404, 422
CHARGING STATION MANAGEMENT | /api/admin/stations/{id} | DELETE | Delete station | Path: id: number | {message: string} | 200 | 400, 401, 403, 404
CHARGER MANAGEMENT | /api/admin/chargers | GET | List all chargers | Query: page?: number, limit?: number, status?: string, station_id?: number, search?: string, sort?: string | {data: Charger[], total: number, page: number, limit: number} | 200 | 401, 403, 422
CHARGER MANAGEMENT | /api/admin/chargers | POST | Onboard new charger | Body: {station_id: number, name: string, model?: string, vendor?: string, serial_number?: string, connectors: ConnectorInput[]} | {charger: Charger, ocpp_url: string, message: string} | 201 | 400, 401, 403, 422
CHARGER MANAGEMENT | /api/admin/chargers/{id} | GET | Get charger details | Path: id: number | {charger: Charger, station: ChargingStation, connectors: Connector[], current_transaction?: Transaction} | 200 | 401, 403, 404
CHARGER MANAGEMENT | /api/admin/chargers/{id} | PUT | Update charger | Path: id: number, Body: {name?: string, model?: string, vendor?: string, latest_status?: string} | {charger: Charger, message: string} | 200 | 400, 401, 403, 404, 422
CHARGER MANAGEMENT | /api/admin/chargers/{id} | DELETE | Remove charger | Path: id: number | {message: string} | 200 | 400, 401, 403, 404
CHARGER MANAGEMENT | /api/admin/chargers/{id}/remote-stop | POST | Stop charging remotely | Path: id: number, Body: {reason?: string} | {success: boolean, message: string, transaction_id?: string} | 200 | 400, 401, 403, 404, 409
CHARGER MANAGEMENT | /api/admin/chargers/{id}/change-availability | POST | Change charger availability | Path: id: number, Body: {type: string, connector_id: number} | {success: boolean, message: string} | 200 | 400, 401, 403, 404
CHARGER MANAGEMENT | /api/admin/chargers/{id}/logs | GET | Get charger OCPP logs | Path: id: number, Query: page?: number, limit?: number, direction?: string, start_date?: string, end_date?: string | {data: OCPPLog[], total: number, page: number, limit: number} | 200 | 401, 403, 404, 422
CHARGER MANAGEMENT | /api/admin/chargers/{id}/status-history | GET | Get status history | Path: id: number, Query: days?: number | {history: StatusHistory[], uptime_percentage: number} | 200 | 401, 403, 404, 422
CUSTOMER MANAGEMENT (CRM) | /api/admin/customers | GET | List all customers | Query: page?: number, limit?: number, search?: string, status?: string, sort?: string | {data: User[], total: number, page: number, limit: number} | 200 | 401, 403, 422
CUSTOMER MANAGEMENT (CRM) | /api/admin/customers/{id} | GET | Get customer details | Path: id: number | {user: User, wallet: Wallet, vehicles: VehicleProfile[], transaction_summary: object} | 200 | 401, 403, 404
CUSTOMER MANAGEMENT (CRM) | /api/admin/customers/{id} | PUT | Update customer | Path: id: number, Body: {full_name?: string, email?: string, is_active?: boolean} | {user: User, message: string} | 200 | 400, 401, 403, 404, 422
CUSTOMER MANAGEMENT (CRM) | /api/admin/customers/{id}/wallet | GET | Get wallet details | Path: id: number | {wallet: Wallet, recent_transactions: WalletTransaction[]} | 200 | 401, 403, 404
CUSTOMER MANAGEMENT (CRM) | /api/admin/customers/{id}/wallet/adjust | POST | Adjust wallet balance | Path: id: number, Body: {amount: number, type: string, description: string} | {wallet: Wallet, transaction: WalletTransaction, message: string} | 200 | 400, 401, 403, 404, 422
CUSTOMER MANAGEMENT (CRM) | /api/admin/customers/{id}/transactions | GET | Customer transactions | Path: id: number, Query: page?: number, limit?: number, start_date?: string, end_date?: string | {data: Transaction[], total: number, total_energy: number, total_amount: number} | 200 | 401, 403, 404, 422
TRANSACTION MANAGEMENT | /api/admin/transactions | GET | List all transactions | Query: page?: number, limit?: number, status?: string, user_id?: number, charger_id?: number, start_date?: string, end_date?: string, sort?: string | {data: Transaction[], total: number, page: number, limit: number, summary: object} | 200 | 401, 403, 422
TRANSACTION MANAGEMENT | /api/admin/transactions/{id} | GET | Get transaction details | Path: id: number | {transaction: Transaction, user: User, charger: Charger, meter_values: MeterValue[], wallet_transactions: WalletTransaction[]} | 200 | 401, 403, 404
TRANSACTION MANAGEMENT | /api/admin/transactions/{id}/stop | POST | Force stop transaction | Path: id: number, Body: {reason: string} | {success: boolean, message: string, final_amount?: number} | 200 | 400, 401, 403, 404, 409
TRANSACTION MANAGEMENT | /api/admin/transactions/{id}/meter-values | GET | Get meter values | Path: id: number | {meter_values: MeterValue[], energy_chart_data: object} | 200 | 401, 403, 404
TARIFF MANAGEMENT (ERP) | /api/admin/tariffs | GET | List all tariffs | Query: page?: number, limit?: number, is_global?: boolean, charger_id?: number | {data: Tariff[], total: number, page: number, limit: number} | 200 | 401, 403, 422
TARIFF MANAGEMENT (ERP) | /api/admin/tariffs | POST | Create new tariff | Body: {rate_per_kwh: number, is_global: boolean, charger_id?: number, name?: string, description?: string} | {tariff: Tariff, message: string} | 201 | 400, 401, 403, 422
TARIFF MANAGEMENT (ERP) | /api/admin/tariffs/{id} | GET | Get tariff details | Path: id: number | {tariff: Tariff, usage_stats?: object} | 200 | 401, 403, 404
TARIFF MANAGEMENT (ERP) | /api/admin/tariffs/{id} | PUT | Update tariff | Path: id: number, Body: {rate_per_kwh?: number, is_global?: boolean, name?: string, description?: string} | {tariff: Tariff, message: string} | 200 | 400, 401, 403, 404, 422
TARIFF MANAGEMENT (ERP) | /api/admin/tariffs/{id} | DELETE | Delete tariff | Path: id: number | {message: string} | 200 | 400, 401, 403, 404
REPORTS & ANALYTICS | /api/admin/reports/charger-uptime | GET | Charger uptime report | Query: charger_id?: number, start_date: string, end_date: string, group_by?: string | {uptime_data: object[], average_uptime: number, total_downtime_hours: number} | 200 | 401, 403, 422
REPORTS & ANALYTICS | /api/admin/reports/energy-delivered | GET | Energy delivery report | Query: charger_id?: number, station_id?: number, start_date: string, end_date: string, group_by?: string | {energy_data: object[], total_energy: number, average_per_session: number} | 200 | 401, 403, 422
REPORTS & ANALYTICS | /api/admin/reports/revenue | GET | Revenue report | Query: charger_id?: number, station_id?: number, start_date: string, end_date: string, group_by?: string | {revenue_data: object[], total_revenue: number, transaction_count: number} | 200 | 401, 403, 422
REPORTS & ANALYTICS | /api/admin/reports/utilization | GET | Charger utilization | Query: charger_id?: number, station_id?: number, start_date: string, end_date: string | {utilization_data: object[], average_utilization: number, peak_hours: object} | 200 | 401, 403, 422
REPORTS & ANALYTICS | /api/admin/reports/transactions | GET | Transaction report | Query: start_date: string, end_date: string, status?: string, user_id?: number, export?: string | {transactions: Transaction[], summary: object, export_url?: string} | 200 | 401, 403, 422
SYSTEM MANAGEMENT | /api/admin/system/health | GET | System health check | None | {status: string, database: string, connected_chargers: number, active_sessions: number, last_updated: string} | 200 | 401, 403
SYSTEM MANAGEMENT | /api/admin/system/logs | GET | System logs | Query: page?: number, limit?: number, level?: string, start_date?: string, end_date?: string | {logs: object[], total: number, page: number, limit: number} | 200 | 401, 403, 422

## Plan
| Focus Area | Tasks / Deliverables | Libraries/ Notes | Deliverables | Status
W0 | Project Setup | Repo setup (Next.js + FastAPI), Render & Vercel CI/CD, ERD for Postgres, Tool setup (Gsheets + Whimsical) | https://github.com/mobilityhouse/ocpp/tree/master
W1 | Wireframes & Auth | Wireframe all Customer & Admin flows, Design login, dashboards, charger lists, Integrate Clerk Auth | Communicating with google - Google EV Location Feed Specification (GELFS) - https://support.google.com/mapcontentpartners/answer/144284#zippy=%2Cev-charging-stations%2Copen-charge-point-interface-ocpi%2Cgoogle-ev-location-feed-specification-gelfs%2Cgelfs-update-types
W2 | OCPP Server & Onboarding | Implement OCPP 1.6 WebSocket skeleton (FastAPI), Charger model & Admin onboarding form (Charger + Station), Charger listing with filter | Test - python -m websockets ws://localhost:9000/cp_id_1 > [2, "12345", "BootNotification", {"chargePointVendor": "The Mobility House", "chargePointModel": "Optimus"}]
W3 | Charger Control & Station Discovery | Admin can activate/deactivate chargers, Charger status logs, Customer: Map view of stations, Display available chargers & specs
W4 | Vehicle Profiles & Wallet UI | CRUD vehicle profiles, Display wallet balance, UI to select vehicle during charge, Backend endpoints for vehicle handling
W5 | Wallet & Razorpay | Razorpay wallet top-up integration, Wallet model & transactions, Deduct amount on charge stop, Display wallet transactions
W6 | Charging Session (Start/Stop) | Customer identifies charger, Starts charge via app (OCPP call), Tracks energy consumed, Implements remote stop & billing
W7 | Session Reports & Invoices | Generate session reports/invoices (HTML/PDF), Store past session data, Admin: View customer charging history
W8 | Billing & Tariff System | Admin: CRUD tariff rates (rs/kWh), Link tariffs to chargers, Calculate billing per session, Admin can view wallet balances
W9 | Admin Reports | Dashboards for uptime, energy delivered, revenue, Per charger reports, Customer usage insights, Frontend charts
W10 | QA & Polish | Unit tests (API/client), Multi-charger scenario testing, Frontend validation, Responsive and accessibility polish
W11 | Staging & Feedback | Deploy to staging, Simulated charge sessions, Internal test feedback, Bug fixing and UX improvements
W12 | Launch & Docs | Final QA, Analytics/logging setup, Production deployment, Developer documentation, Handoff checklist

## KPI
Avg session duration
Charger uptime %
Revenue per charger
Avg wallet top-up amount

## WorkFlows
Flow Name | User Type | User Need | User Action | Device | Device Status OCPP | Server | Remarks
Discovery to Charging | Customer | How do I find available chargers? | Search for charging station on Google Maps |  | Available/ Unavailable / Faulted | Server should be able to continually update chargepoint availability and status using a Google Places API. | If network connectio
|  | Navigate to an available charger? | Use Google Navigate |  | Available/ Unavailable / Faulted
|  | Find free chargers with combatible connectors | User visually confirms availability of chargers, parks in front of said charger. | Device should visually communicate the availabilty and state of the charger through LED lights | Available/ Unavailable / Faulted |  | Not related to CSMS
|  | Connect charger | User physically connects charger to car | Status LED color changes to indicate connection. Device send status change message. (This is only possible if the earlier status was Available). example - [ 2, "12345", "StatusNotification", { "connectorId": 1, "errorCode": "NoError", "status": "Available", "timestamp": "2025-05-15T09:00:00Z", "info": "Connector re-enabled after maintenance", "vendorId": "AcmeEV", "vendorErrorCode": "EVC-000" } ] | Preparing | Server responds with accepted. Logs the message. Then changes the appropriate charger point status to Preparing. | Status is property of the connector not the charger. The DB tables should reflect that .
Device lifecycle | Device | Device does not have network connectivity | Device sets status to Faulted, Sends
Server lifecycle | Server | Server needs to know if a device is connected or not |  |  |  | Server will always verify that all chargers are online. If a charger is not online it is marked as not connected and maintenance is notified.

## Notes
Document | Page | Quote | Remarks
ocpp-1.6 edition 2.pdf | 5 | Central System - Charge Point Management System: the central system that manages Charge Points and has the information for authorizing users for using its Charge Points.
| 5 | Charge Point - The Charge Point is the physical system where an electric vehicle can be charged. A Charge Point has one or more connectors.
| 8 | Due to improvements and new features, OCPP 1.6 is not backward compatible with OCPP 1.5
| 9 | List of all messages
| 11 | When a user wishes to unplug the electric vehicle from the Charge Point, the Charge Point needs to verify that the user is either the one that initiated the charging or that the user is in the same group and thus allowed to terminate the charging. Once authorized, the Charge Point informs the Central System that the charging has been stopped. | Is this relevant? Other unauthorised users are not allowed to unplug chargers. Is there anything that stops a cable from unplugging?
| 11 | A Charge Point MUST NOT send an Authorize.req before stopping a transaction | Special note on stop transaction
| 12 | When a Charge Point needs to be updated with new firmware, the Central System informs the Charge Point of the time at which the Charge Point can start downloading the new firmware. The Charge Point SHALL notify the Central System after each step as it downloads and installs the new firmware. | On handling firmware download
| 12 | In the event of unavailability of the communications or even of the Central System, the Charge Point is designed to operate stand-alone. In that situation, the Charge Point is said to be offline.
| 12 | To improve the experience for users, a Charge Point MAY support local authorization of identifiers, using an Authorization Cache and/or a Local Authorization List.
| 13 | Whether the Local Authorization List is enabled is reported and controlled by the LocalAuthListEnabled configuration key. | Config should be accurate
| 14 | Conflicts between the local authorization list and the validity reported in, for instance, a StartTransaction.conf message might occur. When this happens the Charge Point SHALL inform the Central System by sending a StatusNotification with ConnectorId set to 0, and ErrorCode set to 'LocalListConflict'. | Error method for charger always send status notification. When connectorID is 0 the charger is the proble when connector ID > 1 is has to do with connector
| 15 | The Energy Transfer Period is a period of time during wich energy is transferred between the EV and the EVSE. There MAY be multiple Energy Transfer Periods during a Transaction.
| 15 | A Central System MAY deduce the start and end of an Energy Transfer Period from: the MeterValues that are sent during the Transaction, the status notifications: Charging, SuspendedEV and/or SuspendedEVSE. etc. Central System implementations need to take into account factors such as: Some EVs don’t go to state SuspendedEV: they might continue to trickle charge. Some Charge Point don’t even have a electrical meter.
| 16 | During an EnergyOfferPeriod there may be periods the EV is not charging due to for instance, warm/full battery or EV internal smart charging. | Good shematic
| 16 | During a transaction, there may be periods the EnergyOffer to EV is suspended by the EVSE, for instance due to Smart Charging or local balancing.
| 17 | The Charge Point SHOULD deliver transaction-related messages to the Central System in chronological order as soon as possible. Transaction-related messages are StartTransaction.req, StopTransaction.req and periodic or clock-aligned MeterValues.req messages. | Queuing
| 17 | When offline, the Charge Point MUST queue any transaction-related messages that it would have sent to the Central System if the Charge Point had been online.
| 17 | In the event that a Charge Point has transaction-related messages queued to be sent to the Central System, new messages that are not transaction-related MAY be delivered immediately without waiting for the queue to be emptied. It is therefore allowed to send, for example, an Authorize request or a Notifications request before the transaction-related message queue has been emptied, so that customers are not kept waiting and urgent notifications are not delayed.
| 17 | The delivery of new transaction-related messages SHALL wait until the queue has been emptied. This is to ensure that transaction-related messages are always delivered in chronological order.
| 17 | When the Central System receives a transaction-related message that was queued on the Charge Point for some time, the Central System will not be aware that this is a historical message, other than by inference given that the various timestamps are significantly in the past. It SHOULD process such a message as any other.
| 17 | It is permissible for the Charge Point to skip a transaction-related message if and only if the Central System repeatedly reports a `failure to process the message'. Such a stipulation is necessary, because otherwise the requirement to deliver every transaction-related message in chronological order would entail that the Charge Point cannot deliver any transaction-related messages to the Central System after a software bug causes the Central System not to acknowledge one of the Charge Point’s transaction-related messages.
| 17 | The number of times and the interval with which the Charge Point should retry such failed transaction-related messages MAY be configured using the TransactionMessageAttempts and TransactionMessageRetryInterval configuration keys.
| 17 | When the Charge Point encounters a first failure to deliver a certain transaction-related message, it SHOULD send this message again as long as it keeps resulting in a failure to process the message and it has not yet encountered as many failures to process the message for this message as specified in its TransactionMessageAttempts configuration key. Before every retransmission, it SHOULD wait as many seconds as specified in its TransactionMessageRetryInterval key, multiplied by the number of preceding transmissions of this same message.
| 18 | Connectors numbering (ConnectorIds) MUST be as follows: • ID of the first connector MUST be 1 • Additional connectors MUST be sequentially numbered (no numbers may be skipped) • ConnectorIds MUST never be higher than the total number of connectors of a Charge Point • For operations intiated by the Central System, ConnectorId 0 is reserved for addressing the entire Charge Point. • For operations initiated by the Charge Point (when reporting), ConnectorId 0 is reserved for the Charge Point main controller.
| 19 | Reservation of a Charge Point is possible using the Reserve Now operation. This operation reserves the Charge Point until a certain expiry time for a specific idTag. A parent idTag may be included in the reservation to support ‘group’ reservations. It is possible to reserve a specific connector on a Charge Point or to reserve any connector on a Charge Point. A reservation is released when the reserved idTag is used on the reserved connector (when specified) or on any connector (when unspecified) or when the expiry time is reached or when the reservation is explicitly canceled. | We may need to set up vitual ids for using reservations
| 20 | With Smart Charging a Central System gains the ability to influence the charging power or current of a specific EV, or the total allowed energy consumption on an entire Charge Point / a group of Charge Points, for instance, based on a grid connection, energy availability on the gird or the wiring of a building. Influencing the charge power or current is based on energy transfer limits at specific points in time. Those limits are combined in a Charging Profile.
| 20 | If a transaction-specific profile with purpose TxProfile is present, it SHALL overrule the default charging profile with purpose TxDefaultProfile for the duration of the current transaction only. After the transaction is stopped, the profile SHOULD be deleted. If there is no transaction active on the connector specified in a charging profile of type TxProfile, then the Charge Point SHALL discard it and return an error status in SetChargingProfile.conf. | TxProfile is charging profile specific to the transactions. It can be created as a response to Start Transaction.
| 20 | The Central System imposes charging limits on connectors. In response to a StartTransaction.req PDU The Central System may choose to set charging limits to the transaction using the TxProfile | But charging profile is ususally created to regulate power, not energy.
| 29 | OCPP does not prescribe the use of a specific time zone for time values. However, it is strongly recommended to use UTC for all time values to improve interoperability between Central Systems and Charge Points.
| 29 | Implementations MUST use ISO 8601 date time notation. Message receivers must be able to handle fractional seconds and time zone offsets (another implementation might use them). Message senders MAY save data usage by omitting insignificant fractions of seconds.
| 29 | Charging Session Meter Values - Frequent (e.g. 1-5 minute interval) meter readings taken and transmitted (usually in "real time") to the Central System, to allow it to provide information updates to the EV user (who is usually not at the charge point), via web, app, SMS, etc., as to the progress of the charging session. In OCPP, this is called "sampled meter data", as the exact frequency and time of readings is not very significant, as long as it is "frequent enough".
| 30 | Clock-Aligned Meter Values - Grid Operator might require meter readings to be taken from fiscally certified energy meters, at specific Clock aligned times (usually every quarter hour, or half hour).
| 31 | When the configuration keys: StopTxnAlignedData and StopTxnSampledData are set to an empty string, the Charge Point SHALL not put meter values in a StopTransaction.req PDU.
| 32 | BootNotification - After start-up, a Charge Point SHALL send a request to the Central System with information about its configuration (e.g. version, vendor, etc.). The Central System SHALL respond to indicate whether it will accept the Charge Point.. The Charge Point SHALL send a BootNotification.req PDU each time it boots or reboots. Between the physical power-on/reboot and the successful completion of a BootNotification, where Central System returns Accepted or Pending, the Charge Point SHALL NOT send any other request to the Central System. This includes cached messages that are still present in the Charge Point from before. | OCPP recommends Authorize even when the transaction is initiated by remote. We might not do this.
| 33 | When the Central System responds with a BootNotification.conf with a status Accepted, the Charge Point will adjust the heartbeat interval in accordance with the interval from the response PDU and it is RECOMMENDED to synchronize its internal clock with the supplied Central System’s current time. If the Central System returns something other than Accepted, the value of the interval field indicates the minimum wait time before sending a next BootNotification request. If that interval value is zero, the Charge Point chooses a waiting interval on its own, in a way that avoids flooding the Central System with requests. A Charge Point SHOULD NOT send a BootNotification.req earlier, unless requested to do so with a TriggerMessage.req.
| 33 | If the Central System returns the status Rejected, the Charge Point SHALL NOT send any OCPP message to the Central System until the aforementioned retry interval has expired. During this interval the Charge Point may no longer be reachable from the Central System. It MAY for instance close its communication channel or shut down its communication hardware. Also the Central System MAY close the communication channel, for instance to free up system resources. While Rejected, the Charge Point SHALL NOT respond to any Central System initiated message. the Central System SHOULD NOT initiate any.
| 33 | The Central System MAY also return a Pending registration status to indicate that it wants to retrieve or set certain information on the Charge Point before the Central System will accept the Charge Point. If the Central System returns the Pending status, the communication channel SHOULD NOT be closed by either the Charge Point or the Central System. The Central System MAY send request messages to retrieve information from the Charge Point or change its configuration. The Charge Point SHOULD respond to these messages. The Charge Point SHALL NOT send request messages to the Central System unless it has been instructed by the Central System to do so with a TriggerMessage.req request.
| 33 | While in pending state, the following Central System initiated messages are not allowed: RemoteStartTransaction.req and RemoteStopTransaction.req
| 34 | If a Charge Point needs to send information to the Central System for a function not supported by OCPP, it SHALL use the DataTransfer.req PDU. | CP to CS
| 34 | The vendorId in the request SHOULD be known to the Central System and uniquely identify the vendor-specific implementation. The VendorId SHOULD be a value from the reversed DNS namespace, where the top tiers of the name, when reversed, should correspond to the publicly registered primary DNS name of the Vendor organisation.
| 34 | Charge Point sends a notification to inform the Central System about the status of a diagnostics upload. The Charge Point SHALL send a DiagnosticsStatusNotification.req PDU to inform the Central System that the upload of diagnostics is busy or has finished successfully or failed. The Charge Point SHALL only send the status Idle after receipt of a TriggerMessage for a Diagnostics Status Notification, when it is not busy uploading diagnostics. Upon receipt of a DiagnosticsStatusNotification.req PDU, the Central System SHALL respond with a DiagnosticsStatusNotification.conf.
| 35 | To let the Central System know that a Charge Point is still connected, a Charge Point sends a heartbeat after a configurable time interval. | Central system should keep track of the heartbeats to know that the charge points are connected.
| 35 | Upon receipt of a Heartbeat.req PDU, the Central System SHALL respond with a Heartbeat.conf. The response PDU SHALL contain the current time of the Central System, which is RECOMMENDED to be used by the Charge Point to synchronize its internal clock.
| 35 | The Charge Point MAY skip sending a Heartbeat.req PDU when another PDU has been sent to the Central System within the configured heartbeat interval. This implies that a Central System SHOULD assume availability of a Charge Point whenever a PDU has been received, the same way as it would have, when it received a Heartbeat.req PDU. | So heartbeats are not necessary when we have metervalues.
| 35 | With JSON over WebSocket, sending heartbeats is not mandatory. However, for time synchronization it is advised to at least send one heartbeat per 24 hour. | How do we reliably check if the websocket connection is active?
| 36 | A Charge Point MAY sample the electrical meter or other sensor/transducer hardware to provide extra information about its meter values. It is up to the Charge Point to decide when it will send meter values. This can be configured using the ChangeConfiguration.req message to data acquisition intervals and specify data to be acquired & reported.
| 36 | 1. The id of the Connector from which samples were taken. If the connectorId is 0, it is associated with the entire Charge Point. If the connectorId is 0 and the Measurand is energy related, the sample SHOULD be taken from the main energy meter. 2. The transactionId of the transaction to which these values are related, if applicable. If there is no transaction in progress or if the values are taken from the main meter, then transaction id may be omitted. 3. One or more meterValue elements, of type MeterValue, each representing a set of one or more data values taken at a particular point in time.
| 37 | The Charge Point SHALL send a StartTransaction.req PDU to the Central System to inform about a transaction that has been started. If this transaction ends a reservation (see Reserve Now operation), then the StartTransaction.req MUST contain the reservationId.
| 37 | Upon receipt of a StartTransaction.req PDU, the Central System SHOULD respond with a StartTransaction.conf PDU. This response PDU MUST include a transaction id and an authorization status value.
| 37 | It is likely that The Central System applies sanity checks to the data contained in a StartTransaction.req it received. The outcome of such sanity checks SHOULD NOT ever cause the Central System to not respond with a StartTransaction.conf. Failing to respond with a StartTransaction.conf will only cause the Charge Point to try the same message again as specified in Error responses to transaction-related messages. | in case of IDTag we can send something along with remote start transaction. Start transaction can send the same thing back.
| 39,40,41 | StatusNotification | Possible change in transitions
| 43 | When a transaction is stopped, the Charge Point SHALL send a StopTransaction.req PDU, notifying to the Central System that the transaction has stopped.
| 43 | A StopTransaction.req PDU MAY contain an optional TransactionData element to provide more details about transaction usage. The optional TransactionData element is a container for any number of MeterValues, using the same data structure as the meterValue elements of the MeterValues.req PDU (See section MeterValues)
| 44 | If a transaction is ended in a normal way (e.g. EV-driver presented his identification to stop the transaction), the Reason element MAY be omitted and the Reason SHOULD be assumed 'Local'. If the transaction is not ended normally, the Reason SHOULD be set to a correct value. As part of the normal transaction termination, the Charge Point SHALL unlock the cable (if not permanently attached).
| 45 | Central System can request a Charge Point to change its availability. A Charge Point is considered available (“operative”) when it is charging or ready for charging. A Charge Point is considered unavailable when it does not allow any charging. The Central System SHALL send a ChangeAvailability.req PDU for requesting a Charge Point to change its availability. The Central System can change the availability to available or unavailable
| 45 | When an availability change requested with a ChangeAvailability.req PDU has happened, the Charge Point SHALL inform Central System of its new availability status with a StatusNotification.req as described there.
| 46 | Central System can request a Charge Point to change configuration parameters. To achieve this, Central System SHALL send a ChangeConfiguration.req. This request contains a key-value pair, where "key" is the name of the configuration setting to change and "value" contains the new setting for the configuration setting.
| 47 | If the Central System needs to send information to a Charge Point for a function not supported by OCPP, it SHALL use the DataTransfer.req PDU.
| 48 | Central System can request a Charge Point for diagnostic information. The Central System SHALL send a GetDiagnostics.req PDU for getting diagnostic information of a Charge Point with a location where the Charge Point MUST upload its diagnostic data to and optionally a begin and end time for the requested diagnostic information.
| 49 | Central System can request a Charge Point to start a transaction by sending a RemoteStartTransaction.req. Upon receipt, the Charge Point SHALL reply with RemoteStartTransaction.conf and a status indicating whether it has accepted the request and will attempt to start a transaction. • If the value of AuthorizeRemoteTxRequests is true, the Charge Point SHALL behave as if in response to a local action at the Charge Point to start a transaction with the idTag given in the RemoteStartTransaction.req message. This means that the Charge Point will first try to authorize the idTag, using the Local Authorization List, Authorization Cache and/or an Authorize.req request. A transaction will only be started after authorization was obtained. • If the value of AuthorizeRemoteTxRequests is false, the Charge Point SHALL immediately try to start a transaction for the idTag given in the RemoteStartTransaction.req message. Note that after the transaction has been started, the Charge Point will send a StartTransaction request to the Central System, and the Central System will check the authorization status of the idTag when processing this StartTransaction request.
| 50 | The RemoteStartTransaction.req SHALL contain an identifier (idTag), which Charge Point SHALL use, if it is able to start a transaction, to send a StartTransaction.req to Central System. The transaction is started in the same way as described in StartTransaction. The RemoteStartTransaction.req MAY contain a connector id if the transaction is to be started on a specific connector. When no connector id is provided, the Charge Point is in control of the connector selection. A Charge Point MAY reject a RemoteStartTransaction.req without a connector id.
| 50 | Central System can request a Charge Point to stop a transaction by sending a RemoteStopTransaction.req to Charge Point with the identifier of the transaction. Charge Point SHALL reply with RemoteStopTransaction.conf and a status indicating whether it has accepted the request and a transaction with the given transactionId is ongoing and will be stopped.
| 52 | The Central System SHALL send a Reset.req PDU for requesting a Charge Point to reset itself. The Central System can request a hard or a soft reset. Upon receipt of a Reset.req PDU, the Charge Point SHALL respond with a Reset.conf PDU. The response PDU SHALL include whether the Charge Point will attempt to reset itself.
| 52 | At receipt of a soft reset, the Charge Point SHALL stop ongoing transactions gracefully and send StopTransaction.req for every ongoing transaction. It should then restart the application software (if possible, otherwise restart the processor/controller).
| 52 | At receipt of a hard reset the Charge Point SHALL restart (all) the hardware, it is not required to gracefully stop ongoing transaction. If possible the Charge Point sends a StopTransaction.req for previously ongoing transactions after having restarted and having been accepted by the Central System via a BootNotification.conf. This is a last resort solution for a not correctly functioning Charge Points, by sending a "hard" reset, (queued) information might get lost.
| 52 | In the request the Central System indicates which message it wishes to receive. For every such requested message the Central System MAY optionally indicate to which connector this request applies. The requested message is leading: if the specified connectorId is not relevant to the message, it should be ignored. In such cases the requested message should still be sent.
| 55 | The TriggerMessage.req makes it possible for the Central System, to request the Charge Point, to send Charge Point-initiated messages. In the request the Central System indicates which message it wishes to receive. For every such requested message the Central System MAY optionally indicate to which connector this request applies. The requested message is leading: if the specified connectorId is not relevant to the message, it should be ignored. In such cases the requested message should still be sent.
| 56 | The Charge Point SHALL first send the TriggerMessage response, before sending the requested message. In the TriggerMessage.conf the Charge Point SHALL indicate whether it will send it or not, by returning ACCEPTED or REJECTED. It is up to the Charge Point if it accepts or rejects the request to send. If the requested message is unknown or not implemented the Charge Point SHALL return NOT_IMPLEMENTED.
| 56 | Central System can request a Charge Point to unlock a connector. To do so, the Central System SHALL send an UnlockConnector.req PDU. The purpose of this message: Help EV drivers that have problems unplugging their cable from the Charge Point in case of malfunction of the Connector cable retention. When a EV driver calls the CPO help-desk, an operator could manually trigger the sending of an UnlockConnector.req to the Charge Point, forcing a new attempt to unlock the connector. Hopefully this time the connector unlocks and the EV driver can unplug the cable and drive away.
| 58 | Central System can notify a Charge Point that it needs to update its firmware. The Central System SHALL send an UpdateFirmware.req PDU to instruct the Charge Point to install new firmware. The PDU SHALL contain a date and time after which the Charge Point is allowed to retrieve the new firmware and the location from which the firmware can be downloaded.
| 59 | If it is not possible to continue charging during installation of firmware, it is RECOMMENDED to wait until Charging Session has ended (Charge Point idle) before commencing installation. It is RECOMMENDED to set connectors that are not in use to UNAVAILABLE while the Charge Point waits for the Session to end.

## Review
Charging status color green
Transactions tab in admin console
Diagnostics
SYSadmin vs Station admins
Sanjana
GSM | Without SSL certificate