## Executive Summary
EV Charging Mobile App - Project Estimation
iOS & Android App for OCPP-based EV Charging Management
Team Composition & Hourly Rates
Role | Responsibility | Hourly Rate (₹) | Productivity Boost | Effective Rate (₹)
Senior Developer | Architecture, Code Review, DevOps, Complex Features | 1500 | 20% | 1200
Junior Developer | Development, Testing, AI Pair Programming | 800 | 40% | 480
UI/UX Designer | Wireframes, Mockups, Design System, User Flow | 1000 | 25% | 750
Delivery Manager | Requirements, Delivery Management, QA, Product Management | 1200 | 10% | 1080
Project Effort Summary
Phase | Stories | Total Hours | Duration (Weeks) | Cost (₹)
MVP - P0 (Must Have) | 15 | 286 | 7.2 | ₹241,200
MVP - P1 (Should Have) | 12 | 224 | 5.6 | ₹190,400
MVP - P2 (Nice to Have) | 8 | 112 | 2.8 | ₹95,200
Phase 2 (Future) | 6 | 96 | 2.4 | ₹81,600
TOTAL MVP (P0 + P1) | 27 | 510 | 12.8 | ₹431,600
TOTAL (Including Phase 2) | 41 | 718 | 18 | ₹608,400
Role-wise Hours & Cost Breakdown (MVP)
Role | Hours | Effective Rate (₹/h) | Cost (₹) | % of Total
Senior Developer | 204 | ₹1,200 | ₹244,800 | 40.0%
Junior Developer | 153 | ₹480 | ₹73,440 | 30.0%
UI/UX Designer | 102 | ₹750 | ₹76,500 | 20.0%
Delivery Manager | 51 | ₹1,080 | ₹55,080 | 10.0%
TOTAL | 510 |  | ₹449,820

## Detailed Estimate
Detailed User Stories & Effort Estimation
Phase | Story # | User Story | Senior Dev | Junior Dev | UI/UX | PM/QA | Total Hours
MVP - P0 | 1 | Project Setup: React Native/Capacitor, TypeScript, Git repo | 8 | 4 | 0 | 2 | 14
MVP - P0 | 2 | Authentication: User login/logout with Clerk integration | 6 | 8 | 4 | 2 | 20
MVP - P0 | 3 | API Client: Setup with JWT token management | 8 | 6 | 0 | 2 | 16
MVP - P0 | 4 | QR Scanner: Camera access, QR parsing, charger ID input | 4 | 10 | 6 | 2 | 22
MVP - P0 | 5 | Basic Charging Control: Start/Stop charging buttons | 6 | 8 | 4 | 2 | 20
MVP - P0 | 6 | Wallet Balance Display: Fetch and show wallet balance | 3 | 6 | 4 | 2 | 15
MVP - P0 | 7 | Transaction History: List view with basic details | 4 | 8 | 6 | 2 | 20
MVP - P0 | 8 | User Profile Screen: Display user info, logout option | 3 | 6 | 4 | 2 | 15
MVP - P0 | 9 | Navigation: Bottom tab navigation with 4 screens | 4 | 6 | 8 | 2 | 20
MVP - P0 | 10 | Error Handling: Basic error states and messages | 3 | 6 | 4 | 2 | 15
MVP - P0 | 11 | iOS Configuration: Permissions, build setup | 6 | 4 | 0 | 2 | 12
MVP - P0 | 12 | Android Configuration: Permissions, build setup | 6 | 4 | 0 | 2 | 12
MVP - P0 | 13 | TypeScript Types: API response types and interfaces | 4 | 4 | 0 | 1 | 9
MVP - P0 | 14 | Home Screen: Welcome, quick actions, instructions | 2 | 4 | 6 | 2 | 14
MVP - P0 | 15 | Testing & Bug Fixes (P0): Integration testing | 8 | 12 | 4 | 4 | 28
MVP - P1 | 16 | Razorpay Integration: Native SDK setup for iOS/Android | 10 | 8 | 2 | 3 | 23
MVP - P1 | 17 | Wallet Recharge: Payment flow, verification, UI | 8 | 10 | 6 | 3 | 27
MVP - P1 | 18 | Maps Integration: Leaflet setup, markers, user location | 8 | 12 | 6 | 3 | 29
MVP - P1 | 19 | GPS Station Finder: Geolocation, distance calculation | 6 | 10 | 4 | 3 | 23
MVP - P1 | 20 | Station Details: Bottom sheet with connector info | 4 | 8 | 6 | 2 | 20
MVP - P1 | 21 | Real-time Charging Status: Live updates every 5s | 6 | 8 | 4 | 2 | 20
MVP - P1 | 22 | Live Meter Values: Energy, power, voltage display | 5 | 8 | 5 | 2 | 20
MVP - P1 | 23 | Pull-to-Refresh: Native pull-to-refresh on all screens | 2 | 6 | 4 | 2 | 14
MVP - P1 | 24 | Loading States: Skeletons for all data fetching | 2 | 6 | 6 | 2 | 16
MVP - P1 | 25 | Enhanced Error Handling: Retry logic, better UX | 3 | 6 | 4 | 2 | 15
MVP - P1 | 26 | Session Duration Timer: Live timer during charging | 2 | 4 | 3 | 1 | 10
MVP - P1 | 27 | Testing & Bug Fixes (P1): End-to-end testing | 6 | 10 | 4 | 3 | 23
MVP - P2 | 28 | Station Filter: Filter by connector type, power rating | 4 | 6 | 4 | 2 | 16
MVP - P2 | 29 | Connector Type Display: Icons and compatibility info | 2 | 4 | 4 | 2 | 12
MVP - P2 | 30 | Vehicle Profile: Add/manage vehicle details | 4 | 8 | 6 | 2 | 20
MVP - P2 | 31 | Advanced Transaction History: Filters, export options | 4 | 6 | 6 | 2 | 18
MVP - P2 | 32 | Network Status Indicator: Offline detection banner | 2 | 4 | 3 | 1 | 10
MVP - P2 | 33 | UI Polish: Animations, haptic feedback, refinements | 2 | 6 | 8 | 2 | 18
MVP - P2 | 34 | Charging Cost Estimator: Real-time cost calculation | 3 | 5 | 4 | 2 | 14
MVP - P2 | 35 | Testing & Bug Fixes (P2): Polish and refinement | 4 | 6 | 4 | 2 | 16
Phase 2 | 36 | Push Notifications: FCM setup, charging status alerts | 8 | 10 | 4 | 3 | 25
Phase 2 | 37 | Rewards System: Points, discounts, redemption flow | 6 | 8 | 6 | 3 | 23
Phase 2 | 38 | Multi-language Support: i18n setup, translations | 4 | 6 | 4 | 2 | 16
Phase 2 | 39 | Version Management: Force update, compatibility check | 3 | 5 | 2 | 2 | 12
Phase 2 | 40 | Offline Mode: Local storage, sync when online | 6 | 8 | 3 | 3 | 20
Phase 2 | 41 | Biometric Auth: Fingerprint/Face ID login | 4 | 6 | 2 | 2 | 14